## Sheet1
CG-related | Ballot-weight | Issue Type | Issue key | Issue id | Summary | Reporter | Resolution | Assignee | Status | Updated
| Affirmative | Change Request | FHIR-23820 | 126860 | Consider DiagnosticReport for cancer staging groups | Mark_Kramer | Considered - No action required | may_terry | Resolved - No Change | 2019-11-25 10:26
| Affirmative | Change Request | FHIR-23821 | 126861 | ClinicalImpression might be a better choice for CancerDiseaseStatus than Observation | Mark_Kramer | Considered - No action required | may_terry | Resolved - No Change | 2019-11-25 10:26
| Affirmative | Change Request | FHIR-23822 | 126862 | Consider NCI Thesaurus as a source vocabulary for CancerStagingSystemVS, | Mark_Kramer | Persuasive with Modification | may_terry | Applied | 2019-11-25 10:26
x | Affirmative | Change Request | FHIR-23823 | 126863 | GeneticReport SpecimenType extension is bound to two value sets | Mark_Kramer | Persuasive | may_terry | Duplicate | 2019-11-27 03:19
| Affirmative | Change Request | FHIR-23824 | 126864 | SecondaryCancerCondition should refer to the PrimaryCC using the standard extension condition-dueTo (in R4) | Mark_Kramer | Not Persuasive | may_terry | Resolved - No Change | 2019-11-26 02:21
| Affirmative | Change Request | FHIR-23825 | 126865 | Cardinality showing as optional for fixed-code elements | Mark_Kramer | Persuasive | Mark_Kramer | Applied | 2019-12-15 11:53
| Affirmative | Change Request | FHIR-23826 | 126866 | Inconsistent use of MS flag on required elements | Mark_Kramer | Persuasive with Modification | Mark_Kramer | Applied | 2019-11-25 09:47
| Affirmative | Change Request | FHIR-23827 | 126867 | MedicationStatement.effective should not be required | Mark_Kramer | Persuasive | c.potteiger | Applied | 2019-11-27 02:03
| Affirmative | Change Request | FHIR-23828 | 126868 | Inconsistent reference to sources for definitions | Mark_Kramer | Persuasive with Modification | may_terry | Applied | 2019-11-25 09:48
| Affirmative | Change Request | FHIR-23829 | 126869 | Some value sets missing from the data dictionary | rmartins | Persuasive | c.potteiger | Applied | 2019-11-28 01:23
x | Affirmative | Change Request | FHIR-23830 | 126870 | Genomics report performer should be constrained to Organization only | Mark_Kramer | Not Persuasive |  | Resolved - No Change | 2019-12-04 05:53
| Affirmative | Change Request | FHIR-23831 | 126871 | How is recurrence date captured? | Mark_Kramer | Considered for Future Use | may_terry | Deferred | 2019-11-27 04:29
| Affirmative | Change Request | FHIR-23832 | 126872 | How is recurrence date captured? | Mark_Kramer | Considered for Future Use | may_terry | Duplicate | 2019-11-27 04:29
x | Affirmative | Change Request | FHIR-23833 | 126873 | Data Dictionary items 42b and 42c should be `Genetic Variant Found` instead of `Genetic Variant Tested` | Mark_Kramer | Not Persuasive | c.potteiger | Resolved - No Change | 2019-11-25 10:23
| Affirmative | Change Request | FHIR-23834 | 126874 | Code for TreatmentTerminationReasonVS | Mark_Kramer | Not Persuasive | may_terry | Resolved - No Change | 2019-11-25 10:23
| None | Change Request | FHIR-23865 | 126905 | Different BP profile | smatney | Not Persuasive with Modification | may_terry | Duplicate | 2019-11-27 04:33
| Affirmative | Change Request | FHIR-23913 | 126953 | In this context what does "in the wild" mean? | ldecelles | Persuasive | c.potteiger | Applied | 2019-11-25 10:23
x | Affirmative | Change Request | FHIR-23914 | 126954 | Add new LOINC codes for the genetic tests and panels that do not have LOINC codes | ldecelles | Considered - No action required | may_terry | Resolved - No Change | 2019-11-25 10:23
x | Negative-Major | Change Request | FHIR-23987 | 127027 | GenomicsReport should be derived from the HL7 Genomics Reporting IG | bob.milius | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:37
x | Negative-Major | Change Request | FHIR-23994 | 127034 | Relax cardinality on GenomicsReport category | bob.milius | Persuasive | may_terry | Resolved - change required | 2019-11-27 02:43
x | Negative-Major | Change Request | FHIR-23995 | 127035 | BiologicallyDerivedProduct as possible Subject in GenomicsReport | bob.milius | Not Persuasive | may_terry | Resolved - No Change | 2019-11-25 10:23
x | Negative-Major | Change Request | FHIR-23997 | 127037 | GeneticVariantTested should be derived from Genomics Reporting IG Variant | bob.milius | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:42
x | Negative-Major | Change Request | FHIR-23998 | 127038 | reuse Genomic sReporting IG Region Studied profile | bob.milius |  | may_terry | Duplicate | 2019-12-03 10:53
x | Negative-Major | Change Request | FHIR-23999 | 127039 | GeneticVariantFound should derive from something from the HL7 CG Genomics Reporting IG | bob.milius | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:43
x | Negative-Major | Change Request | FHIR-24000 | 127040 | Align GeneticVariantFound to CG's Variant profile | clemmcdonald | Duplicate | may_terry | Duplicate | 2019-11-28 01:23
x | Affirmative | Change Request | FHIR-24001 | 127041 | clarify what Patient profile is derived from in the Differential view | bob.milius | Persuasive | c.potteiger | Applied | 2019-12-15 11:48
x | Negative-Major | Change Request | FHIR-24002 | 127042 | Do you want to limit to just probe testing? | clemmcdonald | Persuasive with Modification | may_terry | Applied | 2019-12-16 03:08
x | Negative-Major | Change Request | FHIR-24003 | 127043 | add code systems | bob.milius | Persuasive with Modification | may_terry | Applied | 2019-12-16 03:11
x | Negative-Major | Change Request | FHIR-24004 | 127044 | Suggest using CG's RegionStudied profile instead of extension | clemmcdonald |  | may_terry | Duplicate | 2019-12-03 10:54
x | Negative-Major | Change Request | FHIR-24005 | 127045 | clarify ClinVarVS content | bob.milius | Persuasive | may_terry | Applied | 2019-12-16 03:12
x | Affirmative | Change Request | FHIR-24006 | 127046 | Include ClinVar and COSMIC | clemmcdonald | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:21
x | Affirmative | Change Request | FHIR-24007 | 127047 | Point to CG build page | liz.amos | Persuasive | may_terry | Applied | 2019-12-11 01:24
| Affirmative | Change Request | FHIR-24008 | 127048 | Comorbid condition might be better expressed as Observation | clemmcdonald | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:23
x | Affirmative | Change Request | FHIR-24010 | 127050 | Nesting observations | clemmcdonald | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:26
| Affirmative | Change Request | FHIR-24011 | 127051 | Might want to accommodate MedicationDispense | clemmcdonald | Considered for Future Use | may_terry | Resolved - No Change | 2019-11-28 01:23
| Affirmative | Change Request | FHIR-24013 | 127053 | Add Search Parameters and Operations to mCODE | Mark_Kramer | Considered for Future Use | may_terry | Resolved - No Change | 2019-11-25 10:24
| Affirmative | Change Request | FHIR-24015 | 127055 | Does mCODE inherit too much from US Core? | Mark_Kramer | Considered for Future Use | may_terry | Deferred | 2019-12-04 05:47
| Affirmative | Change Request | FHIR-24020 | 127060 | Make meta.profile required? | Mark_Kramer | Not Persuasive | may_terry | Resolved - No Change | 2019-11-25 10:25
| Affirmative | Change Request | FHIR-24021 | 127061 | Should mCODE offer profiles for international use? | Mark_Kramer | Considered for Future Use | may_terry | Deferred | 2019-11-27 04:51
| Affirmative | Comment | FHIR-24032 | 127072 | Overall good work | clemmcdonald | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:23
| Negative-Major | Change Request | FHIR-24033 | 127073 | Should use LOINC code 77304-4 | clemmcdonald | Persuasive | may_terry | Applied | 2019-12-16 03:12
x | Affirmative | Change Request | FHIR-24034 | 127074 | Use CG Region of Interest | clemmcdonald | Persuasive with Modification | may_terry | Duplicate | 2019-11-28 01:23
| Negative-Major | Change Request | FHIR-24036 | 127076 | Use LOINC for Blood Pressure Cuff Size | clemmcdonald | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:23
x | Affirmative | Change Request | FHIR-24038 | 127078 | CG WG using SO codes for Genetic Test Methods | clemmcdonald | Considered for Future Use | may_terry | Deferred | 2019-11-28 01:23
x | Affirmative | Comment | FHIR-24039 | 127079 | Please don't hesitate to request new LOINC codes | clemmcdonald | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:23
x | Affirmative | Change Request | FHIR-24040 | 127080 | Similar to Obs component in CG profile | clemmcdonald | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:23
| Negative-Major | Change Request | FHIR-24457 | 127497 | Unclear how provenance is handled in this IG - MCODE #1 | gdickinson | Persuasive with Modification | Mark_Kramer | Applied | 2019-11-28 01:22
| Negative-Major | Change Request | FHIR-24458 | 127498 | Purpose and intended users should be more clearly stated - MCODE #2 | nedragarrett | Persuasive | c.potteiger | Applied | 2019-12-09 03:54
x | Negative-Major | Change Request | FHIR-24459 | 127499 | Enhance alignment with Clinical Genomics IG - MCODE #3 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:45
| Affirmative | Change Request | FHIR-24460 | 127500 | Consider adding behavioral health/ SDoH elements - MCODE #4 | farrah_khan | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24461 | 127501 | Elixhauer Comorbidity Index equivalent should include ICD/SNOMED as VSAC oids. - MCODE #5 | peter.muir | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:26
x | Affirmative | Change Request | FHIR-24462 | 127502 | Recommend harmonization with Clinical Genomics for sequences. - MCODE #6 | peter.muir | Persuasive with Modification | may_terry | Duplicate | 2019-11-28 01:26
| Affirmative | Change Request | FHIR-24463 | 127503 | Ensure alignment with caDSR and EVS terminologies - MCODE #7 | anita_walden2 | Considered for Future Use | may_terry | Deferred | 2019-11-28 01:26
x | Negative-Major | Change Request | FHIR-24464 | 127504 | NGS vs CEA with NGS - MCODE #8 | apitkus | Persuasive | c.potteiger | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24465 | 127505 | Who is the practitioner for CBCWAutoDifferential? - MCODE #9 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24466 | 127506 | Lab value units and scales - MCODE #10 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24467 | 127507 | Are manual, calculated, etc hematocrits excluded from consideration as this term is only automated HCts? - MCODE #11 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24468 | 127508 | Which morphologies in scope, out of scope? - MCODE #12 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24469 | 127509 | Albumins need to be distinguished by method - MCODE #13 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24470 | 127510 | ASTs need to be differentialed by method - MCODE #14 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24471 | 127511 | Anion gap needs to be distuguished by whether it's calculated based upon 4 or 5 analytes - MCODE #15 | apitkus | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
x | Affirmative | Technical Correction | FHIR-24472 | 127512 | Typo "HGVS" instead of "ClinVar" in VariantFoundIdentifier - MCODE #25 | bheale | Persuasive | may_terry | Applied | 2019-11-28 01:25
x | Affirmative | Comment | FHIR-24473 | 127513 | Multiple profile inheritance (CG WG and US Core) for genomics profiles - MCODE #26 | bheale | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:25
x | Affirmative | Change Request | FHIR-24474 | 127514 | Consider postcoordination of biomarker and associated gene (if one exists) - MCODE #27 | bheale | Considered for Future Use |  | Deferred | 2019-12-04 05:45
x | Negative-Major | Change Request | FHIR-24475 | 127515 | Don't use extension-observation-geneticsgene - MCODE #28 | bheale | Persuasive | may_terry | Applied | 2019-12-11 12:47
x | Negative-Major | Change Request | FHIR-24476 | 127516 | Onco-core-VariantTested-extension is the same as onco-core-GeneticVariantFound - MCODE #29 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:50
x | Affirmative | Question | FHIR-24477 | 127517 | Is annotation of the finding of a variant needed in a minimal data set? - MCODE #30 | bheale | Considered - Question answered | may_terry | Resolved - No Change | 2019-11-28 01:25
x | Negative-Major | Change Request | FHIR-24478 | 127518 | Lacks cytogenetics or structured variant reporting, consider adopting component:cytogenomic-nomenclature in the CG IG - MCODE #31 | bheale | Persuasive | may_terry | Applied | 2019-12-11 12:52
x | Negative-Major | Change Request | FHIR-24479 | 127519 | onco-core-GenomicsReport.html has obf-SpecimenType-extension - why is this here? Why is an extension needed? - MCODE #32 | bheale | Persuasive | may_terry | Duplicate | 2019-11-28 01:25
x | Negative-Major | Change Request | FHIR-24480 | 127520 | Instead of onco-core-RegionStudied-extensionuse another slice on result with a reference to CG IG Regionstudied profile - MCODE #33 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 12:54
x | Negative-Major | Change Request | FHIR-24481 | 127521 | GenomicSourceClass use component from CG IG Observation.component:genomic-source-class - MCODE #34 | bheale | Persuasive | may_terry | Applied | 2019-12-15 07:49
x | Negative-Major | Change Request | FHIR-24482 | 127522 | VariantFoundIdentifier consider Observation.component:variation-code from http://build.fhir.org/ig/HL7/genomics-reporting/obs-variant.html - MCODE #35 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:05
x | Negative-Major | Change Request | FHIR-24483 | 127523 | HGVS data element LOINC code(s) see CG WG IG. - MCODE #36 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:09
x | Affirmative | Change Request | FHIR-24485 | 127525 | consider creating a slice on code or an extension called 'GeneticTestId' or something similar - MCODE #37 | bheale | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:32
| Negative-Major | Change Request | FHIR-24489 | 127529 | IG should conform to latest US Core, QI-Core and CIMI vital sign and lab profiles - MCODE #53 | claude.nanjo | Persuasive with Modification | may_terry | Applied | 2019-12-10 09:47
| Affirmative | Comment | FHIR-24491 | 127531 | This IG is very clean and well done. - MCODE #54 | claude.nanjo | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:21
| Affirmative | Comment | FHIR-24493 | 127533 | References and use of FHIR content appear to be comprehensive and helpful for generating implementations of mCode - MCODE #55 | klsalzman | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Comment | FHIR-24494 | 127534 | What is the current opt in rate for sharing information and what is a likely participation rate? - MCODE #56 | klsalzman | Considered - No action required | Mark_Kramer | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24495 | 127535 | Define acronyms used in use cases - MCODE #57 | klsalzman | Persuasive | c.potteiger | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24496 | 127536 | Observation-BloodPressure extensions should be components and binding strength should be required - MCODE #79 | mclifton | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:26
| Affirmative | Change Request | FHIR-24497 | 127537 | Observation-BodyHeight PreconditionCode could be component and binding strength should be required - MCODE #80 | mclifton | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:26
| Affirmative | Question | FHIR-24498 | 127538 | Observation-BodyHeight BodyPosition typically captured? - MCODE #81 | mclifton | Considered - Question answered | may_terry | Resolved - No Change | 2019-11-28 01:26
| Affirmative | Question | FHIR-24499 | 127539 | Sourcing date of death - MCODE #82 | mrocca | Considered - Question answered | Mark_Kramer | Resolved - No Change | 2019-11-28 01:23
| Affirmative | Question | FHIR-24500 | 127540 | What is the plan for the use cases where a few of the oncology data elements are not captured within an EHR-S? - MCODE #83 | mrocca | Considered - Question answered | Mark_Kramer | Resolved - No Change | 2019-11-28 01:23
| Affirmative | Change Request | FHIR-24501 | 127541 | Recommend reviewing and adding CDISC Therapeutic Area (TA) user guides (focusing on oncology) to existing standards - MCODE #84 | mrocca | Not Persuasive with Modification | may_terry | Applied | 2019-12-16 03:13
| Affirmative | Change Request | FHIR-24502 | 127542 | TradeMark signs missing from several instances of mCODE mentions - MCODE #85 | mrocca | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:23
| Affirmative | Technical Correction | FHIR-24503 | 127543 | Disease Characterization Group - missing period at end of sentence - MCODE #86 | mrocca | Persuasive | c.potteiger | Applied | 2019-11-28 01:23
| Affirmative | Technical Correction | FHIR-24504 | 127544 | Representing Cancer Staging Information - missing period at end of sentence - MCODE #87 | mrocca | Persuasive | c.potteiger | Applied | 2019-11-28 01:23
| Affirmative | Technical Correction | FHIR-24505 | 127545 | [Representing Cancer Staging Information] Minor typo: implementer(s) align. - MCODE #88 | mrocca | Persuasive | c.potteiger | Applied | 2019-11-28 01:23
| Negative-Major | Change Request | FHIR-24506 | 127546 | Clarify IG purpose - MCODE #89 | wendyblumenthal | Persuasive | c.potteiger | Applied | 2019-12-09 03:54
| Negative-Major | Change Request | FHIR-24507 | 127547 | Change definition/wording for disease characterization group - MCODE #90 | wendyblumenthal | Persuasive | c.potteiger | Applied | 2019-11-28 01:26
| Affirmative | Change Request | FHIR-24508 | 127548 | HistologyMorphologyVS link typo - MCODE #91 | wendyblumenthal | Persuasive | c.potteiger | Resolved - change required | 2019-12-15 10:54
| Negative-Major | Change Request | FHIR-24509 | 127549 | Expand SNOMED histology/morphology value set. - MCODE #92 | wendyblumenthal | Persuasive with Modification | may_terry | Applied | 2019-12-15 11:22
| Negative-Major | Change Request | FHIR-24510 | 127550 | Laterality separate required element - MCODE #93 | wendyblumenthal | Persuasive with Modification | may_terry | Applied | 2019-12-16 03:14
| Negative-Major | Change Request | FHIR-24511 | 127551 | Laterality value set change - MCODE #94 | wendyblumenthal | Persuasive with Modification | c.potteiger | Applied | 2019-12-09 03:44
| Affirmative | Change Request | FHIR-24512 | 127552 | Surgical Procedures--reasonCode and reasonReference must be supported - MCODE #95 | wendyblumenthal | Persuasive | Mark_Kramer | Applied | 2019-12-15 07:08
| Affirmative | Change Request | FHIR-24513 | 127553 | Constrained to cancer-related procedures - MCODE #96 | wendyblumenthal | Persuasive | c.potteiger | Applied | 2019-12-03 03:39
| Affirmative | Change Request | FHIR-24514 | 127554 | Radiation procedures--reasonCode and reasonReference must be supported - MCODE #97 | wendyblumenthal | Persuasive | Mark_Kramer | Applied | 2019-12-15 07:10
| Affirmative | Change Request | FHIR-24515 | 127555 | Medication Statement--constrain reasonCode and reasonReference to cancer conditions - MCODE #98 | wendyblumenthal | Persuasive with Modification | c.potteiger | Applied | 2019-12-03 03:39
x | Affirmative | Change Request | FHIR-24516 | 127556 | HER2/neu value missing from value set - MCODE #99 | wendyblumenthal | Persuasive | c.potteiger | Applied | 2019-11-28 01:26
| Affirmative | Change Request | FHIR-24517 | 127557 | Modeling Clinical and Pathologic Staging Groups as Observations - MCODE #100 | wendyblumenthal | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:26
| Negative-Major | Change Request | FHIR-24518 | 127558 | Use BodyStructure rather than extensions - MCODE #101 | lloyd | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:20
| Negative-Major | Change Request | FHIR-24519 | 127559 | Use component rather than extensions - MCODE #102 | lloyd | Persuasive with Modification | may_terry | Resolved - change required | 2019-11-28 01:20
| Affirmative | Change Request | FHIR-24520 | 127560 | Consider using Dosage for radiation - MCODE #103 | lloyd | Not Persuasive with Modification | Mark_Kramer | Applied | 2019-12-11 02:21
| Negative-Major | Change Request | FHIR-24521 | 127561 | Specimen.type already exists (and has the same binding) - MCODE #104 | lloyd | Persuasive | c.potteiger | Applied | 2019-11-28 01:20
| Affirmative | Change Request | FHIR-24522 | 127562 | Propose workflow extensions - MCODE #105 | lloyd | Considered for Future Use | may_terry | Deferred | 2019-12-08 06:32
| Negative-Major | Change Request | FHIR-24523 | 127563 | TreatmentIntent should be handled as a category - MCODE #106 | lloyd | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:20
| Negative-Major | Change Request | FHIR-24524 | 127564 | Removal of dataAbsentReason element from mCode BP profile breaks conformance with base BP profile. - MCODE #107 | ken_sinn | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24525 | 127565 | Removal of component element from mCode BodyHeight profile breaks conformance with base BodyHeight profile. - MCODE #108 | ken_sinn | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24526 | 127566 | Use CIMI blood pressure instead of creating a different one. - MCODE #109 | smatney | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24527 | 127567 | Use CIMI Body Height profile instead of creating a different one - MCODE #110 | smatney | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24528 | 127568 | Use CIMI Body Height profile instead of creating a different one - MCODE #111 | smatney | Duplicate | may_terry | Duplicate | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24529 | 127569 | DataAbsentReason should not be constrained out of CBCWAutoDifferentialPanel and all of its members - MCODE #112 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24530 | 127570 | Extraneous LOINC codes in CBCWAutoDifferentialPanel - MCODE #113 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24531 | 127571 | Consider Subpanels for hemogram and auto differential in CBCWAutoDifferentialPanel - MCODE #114 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24532 | 127572 | CancerDiseaseStatus Observation.code is incorrect - MCODE #115 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Question | FHIR-24533 | 127573 | StatementDateTime extension is redundant with backbone metadata - MCODE #116 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24534 | 127574 | DataAbsentReason should not be constrained out of ComorbidCondition - MCODE #117 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24535 | 127575 | Remove BilirubinDirectMCncPtSerPlasAnLabObs from CMPPanel - MCODE #118 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24536 | 127576 | Align CMP panel with corresponding LOINC structure - MCODE #119 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
x | Negative-Major | Change Request | FHIR-24537 | 127577 | LOINC code for GeneticVariantFound is incorrect - MCODE #120 | smatney | Persuasive | may_terry | Applied | 2019-12-11 01:16
x | Negative-Major | Change Request | FHIR-24538 | 127578 | Align GenticVariantFound profile with LOINC 55233-1 Genetics Analysis Master Panel structure - MCODE #121 | smatney | Not Persuasive |  | Resolved - No Change | 2019-12-04 05:29
x | Affirmative | Change Request | FHIR-24539 | 127579 | Use of experimental LOINC code - MCODE #122 | smatney | Considered for Future Use | may_terry | Resolved - No Change | 2019-11-28 01:25
x | Affirmative | Change Request | FHIR-24540 | 127580 | Category is showing up twice as backbone element - MCODE #123 | smatney | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:25
x | Negative-Major | Change Request | FHIR-24541 | 127581 | LOINC code for GeneticVariantTested is incorrect - MCODE #124 | smatney | Persuasive with Modification | may_terry | Applied | 2019-12-11 01:17
x | Affirmative | Change Request | FHIR-24542 | 127582 | GeneticVariantFound value should only allow for CodeableConcept - MCODE #125 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24543 | 127583 | SpecimenType-extension is unnecessary - MCODE #126 | smatney | Persuasive | may_terry | Duplicate | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24544 | 127584 | Two bindings for SpecimenType-extension - MCODE #127 | smatney | Persuasive | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24545 | 127585 | Adopt the CIMI BodyLocation extension instead of extending bodySite backbone element - MCODE #128 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24546 | 127586 | Remove patient and RelatedPerson as recorders in PrimaryCancerCondition - MCODE #129 | smatney | Persuasive | c.potteiger | Applied | 2019-12-09 03:44
| Affirmative | Change Request | FHIR-24547 | 127587 | CLIA regulations require slicing perfomer for labs - MCODE #130 | smatney | Persuasive with Modification | may_terry | Applied | 2019-12-11 02:20
| Affirmative | Change Request | FHIR-24548 | 127588 | Split TumorMarkerTest into profiles based on result data type - MCODE #131 | smatney | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24549 | 127589 | Inactive concept in BodyWeightPreconditionVS - MCODE #132 | smatney | Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24550 | 127590 | Replace device hierarchy code with procedure hierarchy code in BloodPressureMethodVS - MCODE #133 | smatney | Not Persuasive with Modification | may_terry | Applied | 2019-11-28 01:25
| Affirmative | Change Request | FHIR-24551 | 127591 | Consider expanding RadiationProcedureVS - MCODE #134 | smatney | Considered for Future Use | may_terry | Deferred | 2019-11-28 01:25
| Negative-Major | Change Request | FHIR-24552 | 127592 | Inactive SCT concepts in bodysite-laterality value set - MCODE #135 | smatney | Persuasive | c.potteiger | Applied | 2019-12-09 03:44
| Affirmative | Question | FHIR-24553 | 127593 | Performance scales beyond ECOG and KPS - MCODE #136 | Gonzaga | Considered - No action required | may_terry | Resolved - No Change | 2019-11-28 01:22
| Affirmative | Change Request | FHIR-24554 | 127594 | TNMClinicalStageGroup Observation.code bound to LOINCCodes value set instead of LOINC 75620-5 - MCODE #137 | Gonzaga | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:22
| Affirmative | Change Request | FHIR-24555 | 127595 | TNMPathologicalStageGroup Observation.code bound to LOINCCodes value set instead of 75621-3 - MCODE #138 | Gonzaga | Not Persuasive | may_terry | Resolved - No Change | 2019-11-28 01:22
| Affirmative | Change Request | FHIR-24556 | 127596 | Consider adding biospy to CancerDiseaseStatusEvidenceTypeVS - MCODE #139 | Gonzaga | Persuasive with Modification | c.potteiger | Applied | 2019-12-03 03:38
| Affirmative | Change Request | FHIR-24557 | 127597 | Specify cGy as preferred unit of measurement for TotalRadiationDoseDelivered - MCODE #140 | Gonzaga | Not Persuasive | Mark_Kramer | Resolved - No Change | 2019-11-28 01:22
| Affirmative | Question | FHIR-24558 | 127598 | Where could the name of a chemo protocol be included in MedicationStatement? - MCODE #141 | Gonzaga | Considered - Question answered | may_terry | Resolved - No Change | 2019-11-28 01:22